## Sheet1
Starting Criteria
Week | 7 | Days
Weekly Work | 5 | Days
Weekly Work | 37 | Hours
Prof Dev Module | 0.25 | Proportion of total year effort
Live Project | 0.55 | Proportion of Prof Dev
Effort |  |  |  | Totals |  |  | For Selection |  | For Selection |  | For Selection
Minimum |  |  |  | 5.0875 | Hours per Week |  | Minimum |  | Term |  | Requirements
Expected | 1 | Extra-curricular hours per night |  | 10.0875 | Hours per Week |  | Expected |  | Non-term |  | Design
Stretch | 2 | Extra curricular hours per night |  | 15.0875 | Hours per Week |  | Stretch |  |  |  | Impl
None
|  | Year | Month | Day
Start Date |  | 2018 | 10 | 30 | 2018-10-30
|  |  | Investigation | [6 empty] | 122.1
|  |  | Requirements |  |  | 40.7 | Design |  |  | 81.4 | Implementation | [8 empty] | 202.8 | Release |  |  | 101.05
Team | Gout
|  |  | Term | Term | Term | Term | Term | Term | Term | Term | Non-term | Non-term | Non-term | Term | Term | Term | Term | Term | Term | Term | Term | Term | Term | Term |  | Hours
| Member | Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
|  | Sprint | 1: 0.75; 3: 1.75; 5: 2.75; 7: 3.75; 9: 4.75; 11: 5.75; 13: 6.75; 15: 7.75; 17: 8.75; 19: 9.75; 21: 10.75
|  | Commencing | 2018-10-30 | 2018-11-06 | 2018-11-13 | 2018-11-20 | 2018-11-27 | 2018-12-04 | 2018-12-11 | 2018-12-18 | 2018-12-25 | 2019-01-01 | 2019-01-08 | 2019-01-15 | 2019-01-22 | 2019-01-29 | 2019-02-05 | 2019-02-12 | 2019-02-19 | 2019-02-26 | 2019-03-05 | 2019-03-12 | 2019-03-19 | 2019-03-26 |  | Minimum | Expected | Stretch | Total
| Francis |  | None | None | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Stretch | None | None | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Stretch | None |  | 76.3125 | 0 | 30.175 | 106.4875
| Egg |  | None | None | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Stretch | None | None | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Stretch | None |  | 76.3125 | 0 | 30.175 | 106.4875
| Neo |  | None | None | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Stretch | None | None | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Stretch | None |  | 76.3125 | 0 | 30.175 | 106.4875
| Memphis |  | None | None | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Stretch | None | None | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Stretch | None |  | 76.3125 | 0 | 30.175 | 106.4875
| Hours | Minimum | 0 | 0 | 20.35 | 20.35 | 20.35 | 20.35 | 20.35 | 20.35 | 0 | 0 | 0 | 20.35 | 20.35 | 20.35 | 20.35 | 20.35 | 20.35 | 20.35 | 20.35 | 20.35 | 0 | 0
|  | Expected | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Totals | 305.25 | 0 | 120.7 | 425.95 | Hours
|  | Stretch | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60.35 | 0
| Total Hours | Week | 0 | 0 | 20.35 | 20.35 | 20.35 | 20.35 | 20.35 | 20.35 | 60.35 | 0 | 0 | 20.35 | 20.35 | 20.35 | 20.35 | 20.35 | 20.35 | 20.35 | 20.35 | 20.35 | 60.35 | 0 | Total |  |  | 425.95 |  | Hours
| Total Hours | Sprint | 2018-11-06: 0; 2018-11-20: 40.7; 2018-12-04: 40.7; 2018-12-18: 40.7; 2019-01-01: 60.35; 2019-01-15: 20.35; 2019-01-29: 40.7; 2019-02-12: 40.7; 2019-02-26: 40.7; 2019-03-12: 40.7; 2019-03-26: 60.35 | Total |  |  | 425.95 |  | Hours
You have | 425.95 | Hours, to spend on your project